## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  | 2026-06-07
Project Team Name |  |  | Aimer PAM
Project Topic |  |  | AG News Text Classification
Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75 | D76
 | time axis 2025-06-01 to 2025-08-15
1. Project Kickoff & Research |  |  |  | 2025-06-01 | 2025-06-07 | Vo Hai Dung | Github repo + environment + research notes + Action Plan | Done | bar: 2025-06-01 to 2025-06-07
| 1.1. Environment & repository setup |  |  | 2025-06-01 | 2025-06-02 | Vo Hai Dung | Github repo + virtualenv + tracking | Done | bar: 2025-06-01 to 2025-06-02
|  | 1.1.1. Repository creation |  | 2025-06-01 | 2025-06-01 | Vo Hai Dung | Public Github repo | Done | bar: 2025-06-01
|  |  | 1.1.1.1. Initialize Git repo & branches (main/dev) | 2025-06-01 | 2025-06-01 | Vo Hai Dung | Repo with branches | Done | bar: 2025-06-01
|  |  | 1.1.1.2. Setup folder structure & .gitignore | 2025-06-01 | 2025-06-01 | Vo Hai Dung | Standard folders | Done | bar: 2025-06-01
|  | 1.1.2. Dependency & tracking setup |  | 2025-06-02 | 2025-06-02 | Vo Hai Dung | Tracking workspace ready | Done | bar: 2025-06-02
|  |  | 1.1.2.1. Create virtualenv & install requirements.txt | 2025-06-02 | 2025-06-02 | Vo Hai Dung | Working Python env | Done | bar: 2025-06-02
|  |  | 1.1.2.2. Configure W&B / MLflow workspace | 2025-06-02 | 2025-06-02 | Vo Hai Dung | Workspace linked to repo | Done | bar: 2025-06-02
| 1.2. Literature review |  |  | 2025-06-03 | 2025-06-05 | Vo Hai Dung | Summary of related papers | Done | bar: 2025-06-03 to 2025-06-05
|  | 1.2.1. Read foundational papers (AG News, BERT family) |  | 2025-06-03 | 2025-06-04 | Vo Hai Dung | Foundation notes | Done | bar: 2025-06-03 to 2025-06-04
|  |  | 1.2.1.1. Read AG News dataset paper (Zhang et al.) | 2025-06-03 | 2025-06-03 | Vo Hai Dung | Dataset notes | Done | bar: 2025-06-03
|  |  | 1.2.1.2. Read DeBERTa-v3 & ModernBERT papers | 2025-06-04 | 2025-06-04 | Vo Hai Dung | Architecture notes | Done | bar: 2025-06-04
|  | 1.2.2. Read advanced technique papers |  | 2025-06-05 | 2025-06-05 | Vo Hai Dung | Advanced notes | Done | bar: 2025-06-05
|  |  | 1.2.2.1. Read SetFit & few-shot learning papers | 2025-06-05 | 2025-06-05 | Vo Hai Dung | SetFit notes | Done | bar: 2025-06-05
|  |  | 1.2.2.2. Read mDeBERTa & XLM-R for multilingual | 2025-06-05 | 2025-06-05 | Vo Hai Dung | Multilingual notes | Done | bar: 2025-06-05
| 1.3. Project proposal & planning |  |  | 2025-06-06 | 2025-06-07 | Vo Hai Dung | Detailed Action Plan + risk mitigation | Done | bar: 2025-06-06 to 2025-06-07
|  | 1.3.1. Define scope, objectives & success metrics |  | 2025-06-06 | 2025-06-06 | Vo Hai Dung | Project scope doc | Done | bar: 2025-06-06
|  | 1.3.2. Risk assessment & mitigation strategy |  | 2025-06-07 | 2025-06-07 | Vo Hai Dung | Risk register | Done | bar: 2025-06-07
2. Exploratory Data Analysis (EDA) |  |  |  | 2025-06-08 | 2025-06-14 | Vo Hai Dung | EDA notebook + data analysis report | Done | bar: 2025-06-08 to 2025-06-14
| 2.1. Load and analyze AG News dataset |  |  | 2025-06-08 | 2025-06-10 | Vo Hai Dung | Basic EDA notebook | Done | bar: 2025-06-08 to 2025-06-10
|  | 2.1.1. Class distribution & text length statistics |  | 2025-06-08 | 2025-06-08 | Vo Hai Dung | Statistics table + charts | Done | bar: 2025-06-08
|  |  | 2.1.1.1. Compute class counts & balance ratio | 2025-06-08 | 2025-06-08 | Vo Hai Dung | Class distribution table | Done | bar: 2025-06-08
|  |  | 2.1.1.2. Plot text length histogram per class | 2025-06-08 | 2025-06-08 | Vo Hai Dung | Length distribution charts | Done | bar: 2025-06-08
|  | 2.1.2. Text content visualization |  | 2025-06-09 | 2025-06-10 | Vo Hai Dung | Visualization images | Done | bar: 2025-06-09 to 2025-06-10
|  |  | 2.1.2.1. Generate word clouds for each class | 2025-06-09 | 2025-06-09 | Vo Hai Dung | Word cloud images | Done | bar: 2025-06-09
|  |  | 2.1.2.2. Top n-gram analysis (uni/bi/trigrams) | 2025-06-10 | 2025-06-10 | Vo Hai Dung | N-gram frequency tables | Done | bar: 2025-06-10
| 2.2. Label noise detection with Cleanlab |  |  | 2025-06-11 | 2025-06-12 | Vo Hai Dung | List of suspected noisy labels | Done | bar: 2025-06-11 to 2025-06-12
|  | 2.2.1. Setup Cleanlab pipeline |  | 2025-06-11 | 2025-06-11 | Vo Hai Dung | Cleanlab script | Done | bar: 2025-06-11
|  | 2.2.2. Run analysis & manual review of suspects |  | 2025-06-12 | 2025-06-12 | Vo Hai Dung | Suspected noisy labels (CSV) | Done | bar: 2025-06-12
| 2.3. Topic modeling with BERTopic |  |  | 2025-06-13 | 2025-06-14 | Vo Hai Dung | Topic map of 4 classes | Done | bar: 2025-06-13 to 2025-06-14
|  | 2.3.1. Train BERTopic model on dataset |  | 2025-06-13 | 2025-06-13 | Vo Hai Dung | Trained BERTopic model | Done | bar: 2025-06-13
|  | 2.3.2. Visualize & interpret discovered topics |  | 2025-06-14 | 2025-06-14 | Vo Hai Dung | Interactive topic map (HTML) | Done | bar: 2025-06-14
3. Baseline Models |  |  |  | 2025-06-15 | 2025-06-21 | Vo Hai Dung | Baseline results table for comparison | Done | bar: 2025-06-15 to 2025-06-21
| 3.1. TF-IDF + Logistic Regression / SVM |  |  | 2025-06-15 | 2025-06-17 | Vo Hai Dung | Classic baseline + metrics | Done | bar: 2025-06-15 to 2025-06-17
|  | 3.1.1. Build TF-IDF vectorizer pipeline |  | 2025-06-15 | 2025-06-15 | Vo Hai Dung | Vectorizer artifact | Done | bar: 2025-06-15
|  | 3.1.2. Train Logistic Regression model |  | 2025-06-16 | 2025-06-16 | Vo Hai Dung | LR model + metrics | Done | bar: 2025-06-16
|  | 3.1.3. Train SVM model |  | 2025-06-17 | 2025-06-17 | Vo Hai Dung | SVM model + metrics | Done | bar: 2025-06-17
| 3.2. FastText baseline |  |  | 2025-06-18 | 2025-06-19 | Vo Hai Dung | Trained FastText model + logs | Done | bar: 2025-06-18 to 2025-06-19
|  | 3.2.1. Prepare FastText data format |  | 2025-06-18 | 2025-06-18 | Vo Hai Dung | FastText train file | Done | bar: 2025-06-18
|  | 3.2.2. Train & validate FastText model |  | 2025-06-19 | 2025-06-19 | Vo Hai Dung | FastText model | Done | bar: 2025-06-19
| 3.3. Compare baselines & log to W&B |  |  | 2025-06-20 | 2025-06-21 | Vo Hai Dung | Baseline summary table on W&B | Done | bar: 2025-06-20 to 2025-06-21
|  | 3.3.1. Run all baselines on test set |  | 2025-06-20 | 2025-06-20 | Vo Hai Dung | Test predictions for all models | Done | bar: 2025-06-20
|  | 3.3.2. Build comparison table & log to W&B |  | 2025-06-21 | 2025-06-21 | Vo Hai Dung | W&B dashboard | Done | bar: 2025-06-21
4. Fine-tune Transformer Models |  |  |  | 2025-06-22 | 2025-07-08 | Vo Hai Dung | Model checkpoints meeting O1 (≥0.95 F1) | Done | bar: 2025-06-22 to 2025-07-08
| 4.1. Setup HuggingFace pipeline + tokenizer |  |  | 2025-06-22 | 2025-06-23 | Vo Hai Dung | Reusable training script (train.py) | Done | bar: 2025-06-22 to 2025-06-23
|  | 4.1.1. Install transformers, datasets, accelerate |  | 2025-06-22 | 2025-06-22 | Vo Hai Dung | Configured environment | Done | bar: 2025-06-22
|  | 4.1.2. Write reusable train.py with Trainer API |  | 2025-06-23 | 2025-06-23 | Vo Hai Dung | train.py script | Done | bar: 2025-06-23
| 4.2. Fine-tune DeBERTa-v3-small |  |  | 2025-06-24 | 2025-06-26 | Vo Hai Dung | DeBERTa checkpoint + logs | Done | bar: 2025-06-24 to 2025-06-26
|  | 4.2.1. Prepare data loaders & tokenization |  | 2025-06-24 | 2025-06-24 | Vo Hai Dung | Tokenized DataLoaders | Done | bar: 2025-06-24
|  | 4.2.2. Train & save best checkpoint |  | 2025-06-25 | 2025-06-25 | Vo Hai Dung | DeBERTa checkpoint | Done | bar: 2025-06-25
|  | 4.2.3. Evaluate (test F1 0.9463, below O1) |  | 2025-06-26 | 2025-06-26 | Vo Hai Dung | Validation metrics | Done | bar: 2025-06-26
| 4.3. Fine-tune ModernBERT-base |  |  | 2025-06-27 | 2025-06-29 | Vo Hai Dung | ModernBERT checkpoint + logs | Done | bar: 2025-06-27 to 2025-06-29
|  | 4.3.1. Adapt training script for ModernBERT |  | 2025-06-27 | 2025-06-27 | Vo Hai Dung | Adapted train script | Done | bar: 2025-06-27
|  | 4.3.2. Train & save checkpoints |  | 2025-06-28 | 2025-06-28 | Vo Hai Dung | ModernBERT checkpoint | Done | bar: 2025-06-28
|  | 4.3.3. Evaluate (test F1 0.9471, below O1) |  | 2025-06-29 | 2025-06-29 | Vo Hai Dung | Comparison metrics | Done | bar: 2025-06-29
| 4.4. Hyperparameter tuning |  |  | 2025-06-30 | 2025-07-01 | Vo Hai Dung | Tuning results table | Done | bar: 2025-06-30 to 2025-07-01
|  | 4.4.1. Define search space (LR, BS, epochs) |  | 2025-06-30 | 2025-06-30 | Vo Hai Dung | Search config | Done | bar: 2025-06-30
|  | 4.4.2. Run tuning experiments (Optuna/W&B Sweeps) |  | 2025-07-01 | 2025-07-01 | Vo Hai Dung | Sweep results | Done | bar: 2025-07-01
| 4.5. Scale-up to meet O1 (≥0.95 F1-macro) |  |  | 2025-07-02 | 2025-07-05 | Vo Hai Dung | Larger checkpoints reaching O1 | Done | bar: 2025-07-02 to 2025-07-05
|  | 4.5.1. Fine-tune DeBERTa-v3-base |  | 2025-07-02 | 2025-07-02 | Vo Hai Dung | DeBERTa-v3-base checkpoint (test F1 0.9493) | Done | bar: 2025-07-02
|  | 4.5.2. Fine-tune ModernBERT-large (5 epoch, label smoothing) |  | 2025-07-03 | 2025-07-04 | Vo Hai Dung | ModernBERT-large checkpoint | Done | bar: 2025-07-03 to 2025-07-04
|  | 4.5.3. Confirm O1 reached (val F1 0.9509) & select primary |  | 2025-07-05 | 2025-07-05 | Vo Hai Dung | ModernBERT-large meets O1 | Done | bar: 2025-07-05
| 4.6. Variance-reduction ablation (R-Drop × multi-seed) |  |  | 2025-07-06 | 2025-07-08 | Vo Hai Dung | R-Drop ensemble confirming O1 (F1 0.9528) | Done | bar: 2025-07-06 to 2025-07-08
|  | 4.6.1. Implement RDropTrainer subclass (symmetric KL) |  | 2025-07-06 | 2025-07-06 | Vo Hai Dung | RDropTrainer class | Done | bar: 2025-07-06
|  | 4.6.2. Train 2×3 ablation grid (vanilla × R-Drop on seeds 13/42/73) |  | 2025-07-06 | 2025-07-07 | Vo Hai Dung | 6 checkpoints grid | Done | bar: 2025-07-06 to 2025-07-07
|  | 4.6.3. Run 3-seed soft-voting ensemble inference |  | 2025-07-08 | 2025-07-08 | Vo Hai Dung | Ensemble inference script | Done | bar: 2025-07-08
|  | 4.6.4. Confirm O1 via R-Drop ensemble (F1 0.9528) |  | 2025-07-08 | 2025-07-08 | Vo Hai Dung | O1 confirmed | Done | bar: 2025-07-08
5. Multilingual Extension |  |  |  | 2025-07-09 | 2025-07-22 | Vo Hai Dung | Vietnamese & French 2×2 ablations + tri-lingual benchmark | Done | bar: 2025-07-09 to 2025-07-22
5A. Multilingual Extension (Vietnamese) |  |  |  | 2025-07-09 | 2025-07-15 | Vo Hai Dung | Vietnamese 2×2 ablation + bilingual benchmark | Done | bar: 2025-07-09 to 2025-07-15
| 5A.1. Translate AG News (EN→VI) using OPUS-MT |  |  | 2025-07-09 | 2025-07-10 | Vo Hai Dung | Vietnamese AG News dataset | Done | bar: 2025-07-09 to 2025-07-10
|  | 5A.1.1. Setup OPUS-MT (Helsinki-NLP) pipeline |  | 2025-07-09 | 2025-07-09 | Vo Hai Dung | Translation pipeline | Done | bar: 2025-07-09
|  | 5A.1.2. Batch translate full dataset & validate |  | 2025-07-10 | 2025-07-10 | Vo Hai Dung | Vietnamese AG News (CSV) | Done | bar: 2025-07-10
| 5A.2. Back-translation augmentation (VI→EN→VI) |  |  | 2025-07-11 | 2025-07-12 | Vo Hai Dung | Augmented Vietnamese dataset | Done | bar: 2025-07-11 to 2025-07-12
|  | 5A.2.1. VI→EN translation step |  | 2025-07-11 | 2025-07-11 | Vo Hai Dung | Intermediate English text | Done | bar: 2025-07-11
|  | 5A.2.2. EN→VI back-translation step |  | 2025-07-12 | 2025-07-12 | Vo Hai Dung | Augmented VI dataset | Done | bar: 2025-07-12
| 5A.3. Fine-tune & scale-up to meet O3 (≥0.90 F1) |  |  | 2025-07-13 | 2025-07-14 | Vo Hai Dung | Four VI checkpoints (2×2 ablation) | Done | bar: 2025-07-13 to 2025-07-14
|  | 5A.3.1. Prepare Vietnamese DataLoader |  | 2025-07-13 | 2025-07-13 | Vo Hai Dung | VI DataLoader | Done | bar: 2025-07-13
|  | 5A.3.2. Train mDeBERTa-v3 (vi-only, test F1 0.8863) |  | 2025-07-13 | 2025-07-13 | Vo Hai Dung | mDeBERTa baseline checkpoint | Done | bar: 2025-07-13
|  | 5A.3.3. Train mDeBERTa-v3 + back-translation (0.8960) |  | 2025-07-13 | 2025-07-13 | Vo Hai Dung | mDeBERTa augmented checkpoint | Done | bar: 2025-07-13
|  | 5A.3.4. Scale-up: train XLM-R-large (vi-only + vi+BT) |  | 2025-07-14 | 2025-07-14 | Vo Hai Dung | XLM-R checkpoints meeting O3 | Done | bar: 2025-07-14
|  | 5A.3.5. Evaluate 2×2 ablation; XLM-R+BT 0.9041 meets O3 |  | 2025-07-14 | 2025-07-14 | Vo Hai Dung | VI evaluation report | Done | bar: 2025-07-14
| 5A.4. Evaluate & compare EN vs VI performance |  |  | 2025-07-15 | 2025-07-15 | Vo Hai Dung | Bilingual benchmark report | Done | bar: 2025-07-15
|  | 5A.4.1. Cross-lingual benchmark (EN test on VI model) |  | 2025-07-15 | 2025-07-15 | Vo Hai Dung | Cross-lingual metrics | Done | bar: 2025-07-15
|  | 5A.4.2. Final comparison report (EN vs VI) |  | 2025-07-15 | 2025-07-15 | Vo Hai Dung | Bilingual report | Done | bar: 2025-07-15
5B. Multilingual Extension (French) |  |  |  | 2025-07-16 | 2025-07-22 | Vo Hai Dung | French 2×2 ablation + tri-lingual benchmark | Done | bar: 2025-07-16 to 2025-07-22
| 5B.1. Translate AG News (EN→FR) using OPUS-MT |  |  | 2025-07-16 | 2025-07-17 | Vo Hai Dung | French AG News dataset | Done | bar: 2025-07-16 to 2025-07-17
|  | 5B.1.1. Setup OPUS-MT (Helsinki-NLP) en-fr pipeline |  | 2025-07-16 | 2025-07-16 | Vo Hai Dung | FR translation pipeline | Done | bar: 2025-07-16
|  | 5B.1.2. Batch translate full dataset & validate |  | 2025-07-17 | 2025-07-17 | Vo Hai Dung | French AG News (CSV) | Done | bar: 2025-07-17
| 5B.2. Back-translation augmentation (FR→EN→FR) |  |  | 2025-07-18 | 2025-07-19 | Vo Hai Dung | Augmented French dataset | Done | bar: 2025-07-18 to 2025-07-19
|  | 5B.2.1. FR→EN translation step |  | 2025-07-18 | 2025-07-18 | Vo Hai Dung | Intermediate English text | Done | bar: 2025-07-18
|  | 5B.2.2. EN→FR back-translation step |  | 2025-07-19 | 2025-07-19 | Vo Hai Dung | Augmented FR dataset | Done | bar: 2025-07-19
| 5B.3. Fine-tune mDeBERTa-v3 / XLM-R on French |  |  | 2025-07-20 | 2025-07-21 | Vo Hai Dung | Four FR checkpoints (2×2 ablation) | Done | bar: 2025-07-20 to 2025-07-21
|  | 5B.3.1. Prepare French DataLoader |  | 2025-07-20 | 2025-07-20 | Vo Hai Dung | FR DataLoader | Done | bar: 2025-07-20
|  | 5B.3.2. Train mDeBERTa-v3 (fr-only + fr+BT) |  | 2025-07-20 | 2025-07-20 | Vo Hai Dung | mDeBERTa FR checkpoints | Done | bar: 2025-07-20
|  | 5B.3.3. Scale-up: train XLM-R-large (fr-only + fr+BT) |  | 2025-07-21 | 2025-07-21 | Vo Hai Dung | XLM-R FR checkpoints | Done | bar: 2025-07-21
|  | 5B.3.4. Evaluate all French models (2×2 ablation) |  | 2025-07-21 | 2025-07-21 | Vo Hai Dung | FR evaluation report | Done | bar: 2025-07-21
| 5B.4. Evaluate & compare EN vs VI vs FR |  |  | 2025-07-22 | 2025-07-22 | Vo Hai Dung | Tri-lingual benchmark report | Done | bar: 2025-07-22
|  | 5B.4.1. Cross-lingual benchmark (EN test on FR model) |  | 2025-07-22 | 2025-07-22 | Vo Hai Dung | Cross-lingual metrics | Done | bar: 2025-07-22
|  | 5B.4.2. Final tri-lingual comparison report |  | 2025-07-22 | 2025-07-22 | Vo Hai Dung | Tri-lingual report | Done | bar: 2025-07-22
6. Few-shot Learning with SetFit |  |  |  | 2025-07-23 | 2025-07-25 | Vo Hai Dung | Data efficiency report | Done | bar: 2025-07-23 to 2025-07-25
| 6.1. Setup SetFit + sentence-transformers |  |  | 2025-07-23 | 2025-07-23 | Vo Hai Dung | SetFit script | Done | bar: 2025-07-23
| 6.2. Train with 8/16/32/64 samples/class |  |  | 2025-07-24 | 2025-07-24 | Vo Hai Dung | Accuracy table by sample size | Done | bar: 2025-07-24
| 6.3. Analyze data efficiency, plot learning curve |  |  | 2025-07-25 | 2025-07-25 | Vo Hai Dung | Learning curve chart | Done | bar: 2025-07-25
7. Evaluation & Explainability (XAI) |  |  |  | 2025-07-26 | 2025-08-05 | Vo Hai Dung | Comprehensive evaluation & explanation report | Done | bar: 2025-07-26 to 2025-08-05
| 7.1. Compute Accuracy, F1-macro, Confusion Matrix |  |  | 2025-07-26 | 2025-07-27 | Vo Hai Dung | Complete metrics table | Done | bar: 2025-07-26 to 2025-07-27
|  | 7.1.1. Compute Accuracy & F1-macro for all models |  | 2025-07-26 | 2025-07-26 | Vo Hai Dung | Metrics table | Done | bar: 2025-07-26
|  | 7.1.2. Generate confusion matrix per model |  | 2025-07-27 | 2025-07-27 | Vo Hai Dung | Confusion matrices | Done | bar: 2025-07-27
| 7.2. Confidence calibration (4-calibrator post-hoc grid) |  |  | 2025-07-28 | 2025-07-29 | Vo Hai Dung | Reliability diagrams + ECE 0.0285 | Done | bar: 2025-07-28 to 2025-07-29
|  | 7.2.1. Implement 4 calibrators (baseline / temp-scaling / class-wise isotonic / chained T→isotonic) |  | 2025-07-28 | 2025-07-28 | Vo Hai Dung | 4 calibrator classes | Done | bar: 2025-07-28
|  | 7.2.2. Run calibration grid on validation set |  | 2025-07-28 | 2025-07-28 | Vo Hai Dung | Calibration results | Done | bar: 2025-07-28
|  | 7.2.3. Generate 4 reliability diagrams + bin tables |  | 2025-07-29 | 2025-07-29 | Vo Hai Dung | Reliability diagram plots | Done | bar: 2025-07-29
|  | 7.2.4. Confirm O4 via chained calibrator (ECE 0.0285) |  | 2025-07-29 | 2025-07-29 | Vo Hai Dung | O4 confirmed | Done | bar: 2025-07-29
| 7.3. Benchmark latency and throughput |  |  | 2025-07-30 | 2025-07-30 | Vo Hai Dung | Latency table (ms/sample) | Done | bar: 2025-07-30
| 7.4. SHAP TextExplainer for each class |  |  | 2025-07-31 | 2025-08-01 | Vo Hai Dung | SHAP visualization for hard examples | Done | bar: 2025-07-31 to 2025-08-01
|  | 7.4.1. Setup SHAP TextExplainer |  | 2025-07-31 | 2025-07-31 | Vo Hai Dung | SHAP pipeline | Done | bar: 2025-07-31
|  | 7.4.2. Generate SHAP visualizations for hard examples |  | 2025-08-01 | 2025-08-01 | Vo Hai Dung | SHAP plots | Done | bar: 2025-08-01
| 7.5. LIME local explanation |  |  | 2025-08-02 | 2025-08-03 | Vo Hai Dung | LIME explanation visualization | Done | bar: 2025-08-02 to 2025-08-03
|  | 7.5.1. Setup LIME text explainer |  | 2025-08-02 | 2025-08-02 | Vo Hai Dung | LIME pipeline | Done | bar: 2025-08-02
|  | 7.5.2. Generate LIME explanations for samples |  | 2025-08-03 | 2025-08-03 | Vo Hai Dung | LIME plots | Done | bar: 2025-08-03
| 7.6. Error analysis by class & text length |  |  | 2025-08-04 | 2025-08-04 | Vo Hai Dung | Detailed error analysis report | Done | bar: 2025-08-04
|  | 7.6.1. Analyze errors by class (confusion patterns) |  | 2025-08-04 | 2025-08-04 | Vo Hai Dung | Class error report | Done | bar: 2025-08-04
|  | 7.6.2. Analyze errors by text length & topic |  | 2025-08-04 | 2025-08-04 | Vo Hai Dung | Length/topic error report | Done | bar: 2025-08-04
| 7.7. Long-document inference strategy |  |  | 2025-08-05 | 2025-08-05 | Vo Hai Dung | Sliding-window long-doc inference | Done | bar: 2025-08-05
|  | 7.7.1. Implement sliding-window classifier (src/inference/long_doc.py) |  | 2025-08-05 | 2025-08-05 | Vo Hai Dung | long_doc.py | Done | bar: 2025-08-05
|  | 7.7.2. Mean-pooled softmax aggregation |  | 2025-08-05 | 2025-08-05 | Vo Hai Dung | Aggregation module | Done | bar: 2025-08-05
|  | 7.7.3. Integrate into Gradio app for inputs > 510 tokens |  | 2025-08-05 | 2025-08-05 | Vo Hai Dung | Long-doc Gradio integration | Done | bar: 2025-08-05
8. Demo & Deployment |  |  |  | 2025-08-06 | 2025-08-11 | Vo Hai Dung | Multi-model Gradio app + ONNX model + GitHub release | Done | bar: 2025-08-06 to 2025-08-11
| 8.1. Build Gradio app with SHAP highlight |  |  | 2025-08-06 | 2025-08-08 | Vo Hai Dung | Local-running multi-language Gradio app | Done | bar: 2025-08-06 to 2025-08-08
|  | 8.1.1. Design UI layout (input + output panels) |  | 2025-08-06 | 2025-08-06 | Vo Hai Dung | UI design | Done | bar: 2025-08-06
|  | 8.1.2. Integrate model inference |  | 2025-08-06 | 2025-08-06 | Vo Hai Dung | Working inference | Done | bar: 2025-08-06
|  | 8.1.3. Add SHAP highlight visualization |  | 2025-08-07 | 2025-08-07 | Vo Hai Dung | SHAP-enabled app | Done | bar: 2025-08-07
|  | 8.1.4. 12-model dropdown picker grouped by language |  | 2025-08-07 | 2025-08-07 | Vo Hai Dung | Language-grouped dropdown | Done | bar: 2025-08-07
|  | 8.1.5. Automatic 3-language detection EN/VI/FR (diacritic + token heuristics) |  | 2025-08-07 | 2025-08-07 | Vo Hai Dung | Language auto-detect module | Done | bar: 2025-08-07
|  | 8.1.6. Sliding-window routing for long inputs (Pappagari et al., 2019) |  | 2025-08-08 | 2025-08-08 | Vo Hai Dung | Long-input routing | Done | bar: 2025-08-08
|  | 8.1.7. Project + team logo branding (inline base64) |  | 2025-08-08 | 2025-08-08 | Vo Hai Dung | Branded Gradio UI | Done | bar: 2025-08-08
|  | 8.1.8. 12-model comparison HTML table inside UI |  | 2025-08-08 | 2025-08-08 | Vo Hai Dung | Comparison table in Gradio | Done | bar: 2025-08-08
| 8.2. INT8 deployment + latency Pareto front |  |  | 2025-08-09 | 2025-08-10 | Vo Hai Dung | ONNX models < 200MB + Pareto front | Done | bar: 2025-08-09 to 2025-08-10
|  | 8.2.1. Batch INT8 export of all 12 encoders (scripts/export_all_int8.py) |  | 2025-08-09 | 2025-08-09 | Vo Hai Dung | 12 ONNX INT8 models | Done | bar: 2025-08-09
|  | 8.2.2. Single-stream CPU latency benchmark (scripts/benchmark_all_latency.py) |  | 2025-08-09 | 2025-08-09 | Vo Hai Dung | Single-thread latency table | Done | bar: 2025-08-09
|  | 8.2.3. Multi-thread CPU latency benchmark (12 models) |  | 2025-08-10 | 2025-08-10 | Vo Hai Dung | Multi-thread latency table | Done | bar: 2025-08-10
|  | 8.2.4. Build latency-accuracy Pareto front; identify deployment-tier model (ModernBERT-base) |  | 2025-08-10 | 2025-08-10 | Vo Hai Dung | Pareto front chart | Done | bar: 2025-08-10
|  | 8.2.5. Document O5 as hardware-bounded (batch=1 sequential-bound on commodity x86) |  | 2025-08-10 | 2025-08-10 | Vo Hai Dung | O5 documented | Done | bar: 2025-08-10
| 8.3. Public GitHub release |  |  | 2025-08-11 | 2025-08-11 | Vo Hai Dung | Public GitHub repository | Done | bar: 2025-08-11
|  | 8.3.1. Drop HF Spaces deployment (200 MB free-tier incompatible with 12-model picker UI) |  | 2025-08-11 | 2025-08-11 | Vo Hai Dung | Decision documented | Done | bar: 2025-08-11
|  | 8.3.2. Push code + assets & tag versioned release |  | 2025-08-11 | 2025-08-11 | Vo Hai Dung | Public GitHub release URL | Done | bar: 2025-08-11
| 8.4. Write README + Model Card |  |  | 2025-08-11 | 2025-08-11 | Vo Hai Dung | README.md + Model Card | Done | bar: 2025-08-11
9. Report & Presentation |  |  |  | 2025-08-12 | 2025-08-15 | Vo Hai Dung | Final Report + Slides + Demo Video | Done | bar: 2025-08-12 to 2025-08-15
| 9.1. Write Final Report using SIC template |  |  | 2025-08-12 | 2025-08-13 | Vo Hai Dung | Final Report .docx file | Done | bar: 2025-08-12 to 2025-08-13
|  | 9.1.1. Write Introduction & Background |  | 2025-08-12 | 2025-08-12 | Vo Hai Dung | Intro section | Done
|  | 9.1.2. Write Methodology & Implementation |  | 2025-08-13 | 2025-08-13 | Vo Hai Dung | Methodology section | Done
|  | 9.1.3. Write Results, Discussion & Conclusion |  | 2025-08-13 | 2025-08-13 | Vo Hai Dung | Results section | Done
| 9.2. Create presentation slides |  |  | 2025-08-13 | 2025-08-14 | Vo Hai Dung | Presentation .pptx file | Done | bar: 2025-08-13 to 2025-08-14
|  | 9.2.1. Design slide structure & key takeaways |  | 2025-08-13 | 2025-08-13 | Vo Hai Dung | Slide outline | Done
|  | 9.2.2. Add visualizations & polish design |  | 2025-08-14 | 2025-08-14 | Vo Hai Dung | Polished slides | Done
| 9.5. Demo video script writing (camera shots + voiceover) |  |  | 2025-08-12 | 2025-08-12 | Vo Hai Dung | reports/presentation/demo_video_script.md | Done | bar: 2025-08-12
| 9.6. Logo design (project 4-class symbolism + Aimer PAM) |  |  | 2025-08-12 | 2025-08-12 | Vo Hai Dung | Project logo file | Done | bar: 2025-08-12
| 9.3. Record demo video with background music (~36 seconds) |  |  | 2025-08-14 | 2025-08-14 | Vo Hai Dung | Demo .mp4 file | Done | bar: 2025-08-14
| 9.4. Rehearse presentation & buffer time |  |  | 2025-08-15 | 2025-08-15 | Vo Hai Dung | Ready to present | Done | bar: 2025-08-15